## Slide 1
SISC — Device Experience
Monthly Review Meeting
Global Dashboard · April 2026
4th May 2026

## Slide 2
Meeting Agenda
1
DEX — Overall Executive Summary & Key Metrics
Overview of device experience performance, SLA status, and critical metrics
2
Organization & Operating Model
Team structure, roles, and ownership matrix for device experience
3
DEX — Dashboard
Performance metrics across Intune L3, SCCM L3, App Packaging, AP Ops
4
Team Updates & Highlights
Detailed updates from all 5 teams including wins and challenges
5
Roadmap & Initiatives
Key initiatives, transformation roadmap, and upcoming milestones
6
Risks, Dependencies & Leadership Asks
Critical risks, dependencies, and items requiring leadership decision

## Slide 3
DEX — Overall Executive Summary
125
Intune Tickets
64
W365 Tickets
85
Packaging Requests
40
EU Tickets Logged
40
EU Tickets Logged
Current Focus
Automation and migration remain the main delivery levers
Patch and network dependencies drive most escalations
Autopilot and Cloud PC remain leadership watch areas
Intune L3
Stable
Windows 365
Stable
Application Packaging
Progressing
AP Operations
Stable
SCCM L3
Stable
EU Region
Progressing
In-Progress
Unblock Autopilot networking
Tighten Cloud PC upgrade control
Support AP patching migration
Global Dashboard · April 2026

## Slide 4
Intune L3
Executive Summary
Top MEM Activities — Completed
4 completed
macOS hardening policy implementation as per CIS recommendation
Windows 11 migration completed for AM and AM SOLA OpCos — all systems upgraded
Migrated AZURE AD modules to MgGraph on all production scripts (AZURE AD deprecated)
Device experience SharePoint site created for all tracks (iOS, Android, Windows Autopilot, macOS, W365, MTR)
In-Flight Work
6 in progress
Android Zero Touch (JP): Enable Android Zero Touch enrolment for Japan
macOS device renaming enhancement
Final stages of SMP OpCo migration — close shortly
Completed Mobile device minimum OS compliance for Europe region
Platform SSO implementation for macOS — password-less sign-ins
Microsoft Auto Update (MAU) for Mac — in pipeline
Risks / Mitigation Plan
1 risk
Networking block for Autopilot: Working closely with Networking team to resolve. Mitigation — Working with OPCO network Teams & MS to ensure all network prerequisites are whitelisted.
Ticket Trend — By Category
Chart: 
| Outlook\Teams | RBAC Profile | MacOS | W365 | Office 365 | Windows Autopilot
Tickets | 2 | 7 | 1 | 9 | 7 | 24
Ticket Volume Trend
Chart: 
| Jan | Feb | March | April
Tickets | 103 | 92 | 151 | 125

## Slide 5
Intune L3
Monthly Trend
125
Tickets Received
27
Backlog >14d
4
P1/P2 Incidents
4
Changes Implemented
Automation HUB
4 in progress
Group Tag Automation reviewed and confirmed
Azure Runbooks → Azure Functions migration
BitLocker key backup script in development
Automation for patching UAT windows
Incident vs Work Order — Tickets
Chart: 
| Incidents | WorkOrder | Changes
Incidents | 66 | 57 | 0
Closed | 55 | 44 | 0
Active | 10 | 12 | 0
Microsoft Cases
Chart: 
| Microsoft Cases | Active Cases | Closed
Cases | 12 | 4 | 8
Majority of tickets pending for Autopilot and W365 · MS cases for Autopilot pending

## Slide 6
Windows 365
Executive Summary
Completed Activities
8 completed
Multiple Cloud PC Migrations completed across OpCo's:
AP WNS Opco · MSCSM Opco · SI Opco · SOMEA Opco · GSIRT Opco · EU WNS Opco · Accenture Opco · JSONE Opco
All migrations completed as per schedule.
In-Flight Work
7 in progress
AP Global Protect Service line Implementation
AP to AM device migration for GSD agents
W365 Cloud PC Migration — WNS FAOT, Found Ever EU, WNS Opco
Windows365 Dashboard for All Opco Leads
Global Protect service line — minimizing latency
Ongoing Issues
5 in progress
Slowness in SAP Mozart & File share (WNS-AP)
SAP portal opening for EU WNS users
WNS FAOT Bots enablement in W365 Cloud PC
Frequent W365 disconnection — AP WNS users
AP WNS users cannot access Retailer Status portal
Risks / Mitigation
2 risks
AP WNS users experiencing latency in Share Drive & SAP Mozart · Uncontrolled MS Office version upgrades in W365 Cloud PC
64
↓8%
Tickets Received
3
P1/P2 Incidents
14
Changes Implemented
15
↓3
Backlog >14d
Ticket Volume Trend
Chart: 
| Jan | Feb | Mar | Apr
Tickets | 40 | 35 | 50 | 64
Ticket Trends by Category
Chart: 
| Other issues | Network issues | SAP Issues | App request | VDI Request
Count | 16 | 9 | 17 | 6 | 26

## Slide 7
Application Packaging
Monthly Trends
Top Activities
4 completed
Global/Japan Delivery: 78 global + 7 Japan requests completed; validation checklist reduced rework 10%; Win 11 signed driver packaging pilot successful; 18 apps enabled for 3rd-party auto-updates.
SCCM → Intune Migration: 50 apps migrated, 70 in progress; 18 apps transitioned in April.
Script Modernization: Ongoing migration from batch to PowerShell for automation and Intune integration.
Third-Party Deployments: 18 apps deployed to UAT and Production via Intune with zero issues.
Process Improvements: Centralized intake and tracking dashboard in development.
In-Flight Work
3 in progress
SCCM Retention & Decommissioning: Identify apps to retain and retire those covered by Intune
Intune Migration Challenges: Reviewing complex apps with deployment/exclusion challenges
Batch to PowerShell script conversion, Global & Japan Retirement, ADHOC apps migration
Risks / Mitigation
1 risk
No exclusion condition for Intune app like SCCM. Mitigation — Exclusion Group conditions for Intune apps discussion in progress with Nathan.
85
Requests Received
58
Closed
7.8
Avg Turnaround Time
12
On-Hold
Global Apps HO Trend
Chart: 
| Nov'25 | Dec'25 | Jan'26 | Feb'26 | Mar'26 | Apr'26(till 27th)
Apps | 68 | 61 | 84 | 107 | 100 | 78
Application Count — SCCM → Intune
Chart: 
| Migrated (50) | To be Migrated (70)
Migration | 50 | 70

## Slide 8
SCCM L3
Executive Summary
MECM Activities
8 completed
SSCCM post migration check and verifications
DP/SUP boundary groups reassignments verifications
Application deployment, patch deployment and all MP/DP policy checks
US1 CMG connection point troubleshooting
US1 CMG connection point was down — restored after troubleshooting
Successfully completed post-patch validation on AM production 1 servers
Successfully completed monthly WSUS cleanup on SUP servers
Created custom scripts to improve March month patch compliance
In-Flight Work
5 in progress
Customization of the SISC OpCo patch compliance report
Assisting local IT team with on-site code migration for pending devices
AP rejoin: facing manual patch installation issues on the corporate network — ticket raised with network team
Supported multiple OpCos to resolve OSD issues
Ticket Trend — By Category
Chart: 
| O365 Installer | SCCM Console | Windows Update | SCCM Reports | Device Details | Nagios
Tickets | 1 | 1 | 1 | 2 | 2 | 10
Microsoft Cases
Chart: 
| Microsoft Cases | Active Cases | Closed
Cases | 4 | 1 | 3

## Slide 9
SCCM L3
Monthly Updates
17
Tickets Logged
13
Tickets Closed
816→796
Pending devices for site code migration
69%→80%
Patch compliance
Key Activities
4 completed
Improved pending devices site code migration from AP3 to US1 through Intune package creation
Proactively addressed and resolved OSD issues, improving deployment efficiency
Optimized CN patching compliance — migrated SUP & MP server from AP3 to US1
Quickly addressed US1 site CMG issue, minimizing risk to intranet client operations
In-Flight Work
3 in progress
Assisting local IT team with on-site code migration for pending devices
Customizing SCCM reports to assess patch compliance for SISC OpCo
Content replication optimization
Risks / Mitigation Plan
1 risk
Networking blocking issue on AP Windows servers impacting Windows updates. Mitigation — Working with MS and Network team to identify the cause.
Role Distribution — Incidents & Work Orders
Chart: 
| Workload 1 | Workload 2 | Workload 3
Inc-Pending | 1 | 0 | 0
Inc-Closed | 0 | 0 | 8
WO-Pending | 4 | 0 | 0
WO-Closed | 0 | 0 | 14
Trend — April 2026
Chart: 
| 1 Apr | 8 Apr | 15 Apr | 22 Apr | 30 Apr
Incidents | 4 | 3 | 1 | 1 | 2
Work Orders | 0 | 3 | 3 | 3 | 4

## Slide 10
AP Operations
Monthly Updates
38
Tickets
19.5%
Current PD
6
Op-Cos live with Autopilot
Key Activities
3 completed
Windows Autopilot: 1 new Op-Co (STT) onboarded; ~10% adoption achieved across AP.
Windows Hello for Business: PIN enforcement in progress; live in SISC, testing ongoing for other Op-Cos.
Patch Debt & Vulnerabilities: Increase in vulnerabilities due to BIOS update limitations; remediation in progress. Multiple high sev vulns addressed to keep PD under 15%.
Network Enablement: Working with Network team to enable required endpoints for seamless Intune updates.
Windows Hello PIN Enablement
8021
Autopilot Enrollments — Apr 26
210
In-Flight Priorities
2 in progress
Work with Global team for Patching migration schedule: Setup schedule for patching migration to Intune & movement of required Op-Cos in timely manner
Continue Autopilot Adoption: Work on Go-Live of multiple high-volume Op-Cos like SID & SOEMKL
Reduction of PD: Under revised KPI & Thresholds. Patching Migration — SCCM to Intune test to be initiated
Risks / Mitigation Plan
2 risks
RAS issue due to device non-compliant devices. Mitigation: Root cause via rejoin/enroll into Intune in progress — likely due to device activity.
SWING Authentication issues for 3 OPCO's (SOMAS, PENTAS). Mitigation: Working with Microsoft to identify root cause — SWING connecting with Device cert but not User Cert.
Regional PD Trend
Chart: 
| January | February | March | April
PD% | 16.5 | 15.5 | 17.5 | 19.5
Autopilot Device Count
Chart: 
| January | February | March | April
Devices | 1930 | 2100 | 2300 | 2605

## Slide 11
EU Region
Monthly Update
12.5%→9.1%
EU Patch Debt
40
Tickets Logged
32
Tickets Closed
Role Distribution — Incidents & Work Orders
Chart: 
| Client Config Analyst | Client Architect | IT Service Owner
Inc-Pending | 1 | 0 | 1
Inc-Closed | 0 | 0 | 6
WO-Pending | 4 | 0 | 0
WO-Closed | 1 | 11 | 14
Trend — April 2026
Chart: 
| 1 Apr | 8 Apr | 15 Apr | 22 Apr | 30 Apr
Incidents | 0 | 2 | 4 | 6 | 10
Work Orders | 5 | 12 | 22 | 35 | 44
EUSP — Client Configuration Analyst
SSS-EU Leavers & New joiners (2026 March) requests processed by adding computers to respective AD groups
Adobe latest version v26.001.21411 provided to Sony Music
EU Patch debt decreased to 9.1% from 12.5%
33 critical Google Chrome vulnerabilities fixed
EUSP — Client Architect
GPO - GISNWA: Security Changes Windows 10 policy causing Network discovery failure — SSDP Discovery set to disabled
GPO - SSDP discovery enabled and applied on test OU — awaiting confirmation from test user
SDS/BE-Brussels: Legacy LAPS not working for the opco — policies re-mapped
RDP/Admin access audit for EU region completed
EUSP — IT Service Owner
Removed Europe Intune compliance exception group to enforce global minimum OS requirements
Disabled and deleted unused Helix resolver group — reassigning 40 stuck tickets to avoid delays
Investigating Autopilot issue affecting Teams & SharePoint thumbnail rendering — Microsoft engaged

## Slide 12
DEX — SIE
Executive Summary
25/25
Tickets Closed
100%
Within SLA
Zero
Backlog Maintained
Key Outcomes
Windows Hello authentication fully restored with NGC reprovisioning and trust chain validation completed
SCEP/NDES/CA infrastructure validation completed with end-to-end certificate chain verified to Sony Global Root CA 2
Ivanti and CrowdStrike security platforms successfully deployed — completing critical security baseline requirements
Fleet and Okta Verify workstreams advanced with Windows Autopilot deployment progressing through delegated SCEP challenge validation
Performance & Progress
All 25 tickets closed within SLA — 100% closure rate exceeding the 95% target
Poly Teams sign-out investigation continues with active collaboration between Microsoft and Poly engineering teams
Conditional Access and Trusted Location subnet validation pending — 17 policies reviewed
Overall service status maintained at Green with operational control demonstrating readiness for platform expansion
Next Quarter Priorities
Close remaining Conditional Access and Poly investigation with root cause analysis for Teams sign-out issues
Complete subnet validation and policy refinement to finalize Trusted Location validation and Conditional Access policy updates
Continue Fleet and Okta Verify validation advancing Windows Autopilot deployment with delegated SCEP challenge protocols
Current Focus
Security Baseline & Hardening: Enterprise security alignment. SLA Excellence: 99% closure rate. Profile Governance: Certificate, Wi-Fi, VPN automated monitoring. Executive Reporting: Bi-weekly service health reporting.
SIE Ticket Volume
Chart: 
| Feb | March | April
Closed Incidents | 7 | 19 | 25
Total Incidents | 7 | 19 | 25